## 90-Day Project Plan
90-Day Fabric Deployment Project Plan
Fabric Fast Track Workbook · Raleigh Day of Data 2026 · jonathan.stewart@soundbi.com
Yellow = your input ¦ Green = auto-calculated ¦ Enter Start Date in B4 — all milestone dates update automatically
Project: |  |  |  |  | Organization:
Start Date (Day 1): |  |  |  |  | Target Go-Live (Day 90):
Executive Sponsor: |  |  |  |  | Data Team Lead:
PHASE 1 — ASSESS (Days 1–15) ¦ Goal: Know what you have, who cares, and what success looks like ¦ Owner: Head of Data + IT Lead
| Day | Calendar Date | Milestone | Owner | Status | Notes
| 1 |  | Kickoff — project charter signed, sponsor confirmed |  |  |  | ☐
| 1–5 |  | Data source inventory started |  |  |  | ☐
| 5 |  | Executive sponsor named and briefed |  |  |  | ☐
| 7 |  | Primary use case defined with Day 90 measurable outcome |  |  |  | ☐
| 10 |  | Stakeholder map complete |  |  |  | ☐
| 12 |  | Data source inventory complete — quality ratings assigned |  |  |  | ☐
| 14 |  | Capacity sizing reviewed and approved |  |  |  | ☐
| 15 |  | Acceptance criteria framework shared with business owner |  |  |  | ☐
🔒 PHASE 1 GATE — Day 15 (all items must pass to proceed)
| Gate Item |  |  | Owner | Status |  | Date Signed
| Executive sponsor named and has attended at least one meeting |  |  |  | ☐ Pass ☐ Hold
| Use case has a written, measurable Day 90 outcome |  |  |  | ☐ Pass ☐ Hold
| Capacity sizing approved by IT and finance |  |  |  | ☐ Pass ☐ Hold
Gate signed by:
PHASE 2 — GOVERN (Days 15–25) ¦ Goal: Define the rules before anything is built ¦ Owner: Platform Admin + Security Team
| Day | Calendar Date | Milestone | Owner | Status | Notes
| 16 |  | Workspace naming convention drafted |  |  |  | ☐
| 17 |  | Security model decision meeting (RLS, SP, promotion rights) |  |  |  | ☐
| 18 |  | Naming convention approved by IT |  |  |  | ☐
| 18 |  | Security matrix completed and signed |  |  |  | ☐
| 20 |  | Fabric capacity assigned to domain |  |  |  | ☐
| 21 |  | Service principal provisioned and tested in dev |  |  |  | ☐
| 22 |  | Deployment pipeline (dev → test → prod) configured |  |  |  | ☐
| 24 |  | Deployment pipeline tested end-to-end |  |  |  | ☐
🔒 PHASE 2 GATE — Day 25 (all items must pass to proceed)
| Gate Item |  |  | Owner | Status |  | Date Signed
| Workspace naming convention documented and IT-approved |  |  |  | ☐ Pass ☐ Hold
| Security model approved — roles mapped before any item created |  |  |  | ☐ Pass ☐ Hold
| One Fabric deployment pipeline runs end-to-end, no manual steps |  |  |  | ☐ Pass ☐ Hold
Gate signed by:
PHASE 3 — LAND (Days 25–50) ¦ Goal: Get clean, structured data flowing reliably ¦ Owner: Data Engineering Team
| Day | Calendar Date | Milestone | Owner | Status | Notes
| 25 |  | Medallion matrix completed for all sources |  |  |  | ☐
| 26 |  | Pipeline development begins — quality 3–5 sources first |  |  |  | ☐
| 28 |  | First bronze pipeline running and monitored |  |  |  | ☐
| 35 |  | Bronze flowing for all quality 3–5 sources |  |  |  | ☐
| 38 |  | Quality 1–2 sources remediated and in bronze |  |  |  | ☐
| 40 |  | All sources in bronze |  |  |  | ☐
| 42 |  | Silver transformations underway |  |  |  | ☐
| 45 |  | Silver complete — all joins, dedup, type conformance |  |  |  | ☐
| 48 |  | First gold tables built |  |  |  | ☐
| 50 |  | Business owner previews at least one gold table |  |  |  | ☐
🔒 PHASE 3 GATE — Day 50 (all items must pass to proceed)
| Gate Item |  |  | Owner | Status |  | Date Signed
| Bronze data landing on schedule for all sources |  |  |  | ☐ Pass ☐ Hold
| Silver validated against source (row counts + spot checks) |  |  |  | ☐ Pass ☐ Hold
| At least one gold table previewed and confirmed by business owner |  |  |  | ☐ Pass ☐ Hold
Gate signed by:
PHASE 4 — BUILD (Days 50–75) ¦ Goal: Turn validated data into reports that pass business review ¦ Owner: BI Developer + Business Analyst
| Day | Calendar Date | Milestone | Owner | Status | Notes
| 50 |  | Acceptance criteria reviewed with business owner |  |  |  | ☐
| 52 |  | Semantic model connected to gold layer |  |  |  | ☐
| 55 |  | BPA audit run — zero critical violations, warnings documented |  |  |  | ☐
| 58 |  | RLS roles configured and tested |  |  |  | ☐
| 60 |  | First reports built against semantic model |  |  |  | ☐
| 62 |  | First UAT pass — business owner tests independently |  |  |  | ☐
| 65 |  | All reports in UAT |  |  |  | ☐
| 70 |  | UAT complete — discrepancies resolved |  |  |  | ☐
| 74 |  | All reports approved, Phase 4 gate ready |  |  |  | ☐
🔒 PHASE 4 GATE — Day 75 (all items must pass to proceed)
| Gate Item |  |  | Owner | Status |  | Date Signed
| Business owner signed off on at least 3 reports |  |  |  | ☐ Pass ☐ Hold
| BPA audit: zero critical violations |  |  |  | ☐ Pass ☐ Hold
| RLS validated by someone who is not the developer |  |  |  | ☐ Pass ☐ Hold
Gate signed by:
PHASE 5 — OPERATE (Days 75–90) ¦ Goal: Hand off a running platform, not a delivered project ¦ Owner: Platform Team + Business Owners jointly
| Day | Calendar Date | Milestone | Owner | Status | Notes
| 75 |  | Monitoring alerts configured (pipeline, refresh, self-alert) |  |  |  | ☐
| 77 |  | Operational runbook drafted |  |  |  | ☐
| 78 |  | Runbook reviewed by IT lead and business owner |  |  |  | ☐
| 80 |  | Capacity baseline documented (normal operating range) |  |  |  | ☐
| 82 |  | Business owner completes self-service navigation — no IT assist |  |  |  | ☐
| 85 |  | Business owner trains one colleague independently |  |  |  | ☐
| 87 |  | Go-live — deployment pipeline promotes to production |  |  |  | ☐
| 88 |  | Day 1 post go-live health check |  |  |  | ☐
| 90 |  | Formal handoff — all three parties sign go-live checklist |  |  |  | ☐
🔒 PHASE 5 GATE — Day 90 (all items must pass to proceed)
| Gate Item |  |  | Owner | Status |  | Date Signed
| Go-live checklist signed by sponsor, IT lead, and business owner |  |  |  | ☐ Pass ☐ Hold
| At least one business owner demonstrated self-service — no IT assist |  |  |  | ☐ Pass ☐ Hold
| Runbook reviewed and first on-call person has read it |  |  |  | ☐ Pass ☐ Hold
Gate signed by:
90-DAY SUMMARY DASHBOARD (fill in at Day 90 review)
Go-live date
| Phases completed on time |  |  |  | 5 of 5
| Gates passed first attempt |  |  |  | 5 of 5
Gates that required a hold
Reports delivered
Business owners trained
Payback week (target: Week 11)
Manual hours eliminated/week
Fabric Fast Track Workbook · Raleigh Day of Data 2026 · jonathan.stewart@soundbi.com · LinkedIn: /in/sqllocks

## Weekly Check-In
Weekly Sponsor Check-In — Standing Agenda
30 minutes · every week · Data Lead + Business Owner · No exceptions
"The weekly 30-minute check-in is the highest-ROI meeting in the 90-day deployment."
| # | Agenda Item | Discussion Prompt | Owner / Action
| 1 | Status vs. plan | Are we on the day-number timeline? If not, what is the specific gap and who owns closing it?
| 2 | What we're building next week | Does this match the business owner's mental model? Any surprises?
| 3 | Blockers needing sponsor escalation | Name them explicitly. Assign owner and resolution date. Don't let them age past one week.
| 4 | One thing the business owner does before next meeting | Keep engagement continuous. Never leave with nothing assigned to the business owner.
Notes / Parking Lot
Fabric Fast Track Workbook · Raleigh Day of Data 2026 · jonathan.stewart@soundbi.com · LinkedIn: /in/sqllocks